## Exception Report 2009-08-07
No. | Weekly Update Report Exception Data
| Agency Name: | Department of Homeland Security |  | Current Date: | 2009-08-11
| Week End Date: | 2009-08-11 |  | Previous Date: | 2009-08-04
| Agency/Bureau | TAFS | Sub-Account Code (OPTIONAL) | Current Obligations | Previous Obligations | Difference | Current Gross Outlays | Previous Gross Outlays | Difference
1 | (024-58) Department of Homeland Security: Customs and Border Protection | (70-0535 2009 \ 2010) Construction, Customs and Border Protection - Recovery Act |  | 214121912 | 214121912 | 0 | 678284 | 614300 | 63984
2 | (024-58) Department of Homeland Security: Customs and Border Protection | (70-0536 2009 \ 2010) Border Security Fencing, Infrastructure, and Technology - Recovery Act
3 | (024-55) Department of Homeland Security: Immigration and Customs Enforcement | (70-0546 2009 \ 2010) Automation Modernization, Immigration and Customs Enforcement - Recovery Act
4 | (024-45) Department of Homeland Security: Transportation Security Administration | (70-0556 2009 \ 2010) Aviation Security - Recovery Act |  | 121479126 | 120386579 | 1092547 | 20450891 | 20450236 | 655
5 | (024-60) Department of Homeland Security: United States Coast Guard | (70-0618 2009 \ 2010) Alteration of Bridges - Recovery Act |  | 51060564 | 51060564 | 0
6 | (024-60) Department of Homeland Security: United States Coast Guard | (70-0617 2009 \ 2010) Acquisition, Construction, and Improvements - Recovery Act |  | 7473838 | 7473838 | 0
7 | (024-70) Department of Homeland Security: Federal Emergency Management Agency | (70-0708 2009 \ 2010) Emergency Food and Shelter - Recovery Act |  |  |  |  | 56009968 | 40698184 | 15311784
8 | (024-70) Department of Homeland Security: Federal Emergency Management Agency | (70-0567 2009 \ 2010) Firefighter Assistance Grants - Recovery Act
9 | (024-20) Department of Homeland Security: Office of the Inspector General | (70-0201 2009 \ 2012) Office of Inspector General - Recovery Act
10 | (024-10) Department of Homeland Security: Departmental Management and Operations | (70-0118 2009 \ 2010) Office of the Under Secretary for Management - Recovery Act
11 | (024-58) Department of Homeland Security: Customs and Border Protection | (70-0534 2009 \ 2010) Salaries and Expenses, Customs and Border Protection - Recovery Act |  | 1959603 | 1959603 | 0 | 12517 | 12517 | 0
12 | (024-70) Department of Homeland Security: Federal Emergency Management Agency | (70-0563 2009 \ 2010) State and Local Programs - Recovery Act |  | 77811975 |  | 77811975
New Actions Taken |  |  |  | New Actions Planned
CBP: |  |  |  | CBP:
Closed the public comment period of the Draft Environmental Assessments for the following land Ports of Entry (LPOEs) on August 8, 2009. - Walhalla, ND - Neche, ND - Churubusco, NY - Maida, ND - Morgan, MT. Submitted congressional notifications to DHS regarding the upcoming award of 7 design/build contracts through an interagency agreement (IAA) with GSA on August 6, 2009. Issued request for quotations (RFQ) for repair and alteration (R&A) installments of emergency generators on August 7, 2009. Received concurrence on August 6, 2009 for the consultation letter sent to the New York US Fish and Wildlife Service (FSW) field office for the Churubusco and Cannon Corners LPOEs. |  |  |  | Plans to modify the current IAA with GSA for approximately $11.27 million to account for an additional design/build construction project at Maida, ND LPOE as early as the week of August 10, 2009. Plans to issue the Request for Proposals (RFP) as early as the week of August 10, 2009 for the Maida design/build construction under the GSA IAA. Plans to award seven design/build contracts through GSA IAA for modernization of CBP-owned ports as early as August 13, 2009. Plans to issue RFQs the Border Security Deployment Program (BSDP) installations as early as August 14, 2009. Plans to issue RFPs for emergent repairs as early as August 13, 2009. Plans to initiate land appraisals for design/build modernization projects as early as August 10, 2009. Plans to modify the IAA with US Army Corps of Engineers (USACE) as early as the week of August 10, 2009 for approximately $350,000 to provide environmental remediation to address existing firing ranges at the following LPOEs: - Noonan, ND - Whitetail, MT - Antelope Wells, NM. Plans to close the public comment period of the Draft Environmental Assessments for the following LPOEs on August 13, 2009: - Pinnacle Road, VT - Pittsburg, NH - Wild Horse, MT - Scobey, MT - Antelope Wells, NM. Plans to issue a presolicitation notice as early as August 10, 2009, in order to notify small business contractors of the six direct procurements of design/build contractor services for ARRA modernization projects at the following LPOEs: - Boundary, WA - Los Ebanos, TX - Morses Line, VT - Hamlin, ME - Del Bonita, MT - Cannons Corner, NY. Plans to issue an RFP as early as August 13, 2009 for Phase 1 of a two-phased solicitation for the six direct procurements of design/build contractor services for ARRA modernization projects at the following LPOEs: - Boundary, WA - Los Ebanos, TX - Morses Line, VT - Hamlin, ME - Del Bonita, MT - Cannons Corner, NY.
CBP: |  |  |  | CBP:
No new actions taken to report this week. |  |  |  | An internal Acquisition Strategy Review for Mobile Surveillance Systems (MSS) will be conducted during the week of August 17, 2009.
ICE: |  |  |  | ICE:
Completed engineering analysis to develop a plan of action and milestones to interface ICE tactical communications systems with DHS OneNet |  |  |  | Continue technical analysis and procurement planning for the modernization of communications systems in the Boston and Denver Regions
Modified the procurement evaluation plan for the Stimulus Hub Upgrade Generator System procurement and re-submitted the document to OAQ |  |  |  | As necessary, continue to perform edits to procurement packages based on feedback from the ICE OAQ review process
Modified the procurement evaluation plan for the Region 2 and 3 Equipment and Limited Services procurement and re-submitted the document to OAQ |  |  |  | Tailor the procurement evaluation plan for the Stimulus Hub Upgrade Equipment procurement and re-submit the document to OAQ
Submitted a list of the GSA IT Schedule 70 vendors that provide the equipment required for the Stimulus Tactical Communications Equipment and Limited Services procurement to the Office of Acquisition Management (OAQ) |  |  |  | CBP:
Briefed DHS HQ on ICE's internal controls regarding ARRA Reporting/Funding |  |  |  | Tactical Communications: - CBP is waiting for release of the Acquisition Decision Memorandum by DHS Chief Procurement Officer to the TACCOM Program Manager. Non-Intrusive Inspection (NII) - The Technical Evaluation Board will convene on August 12, 2009 to begin the evaluation of all proposals in response to the ARRA RFQs.
Mobile Command Vehicles (1583) RFP issued on Thursday, 8/6/09
TSA:
Secretary Napolitano announced approx $42 million in ARRA funding for the construction of new inline baggage handling systems at Sacramento International Airport (SMF), Honolulu International Airport (HNL) and Kahului Airport (OGG) on 8/7/09. Obligated approximately $1.08M for Airport Surveillance Program-CCTV equipment at Boise, Idaho (BOI) in an OTA signed 7/27/09.
USCG:
Pre-bid meeting of Galveston Bridge was held on August 6, 2009 in Galveston, TX.
Pre-construction meeting of Burlington Bridge was held on August 7, 2009 in Kansas City, Missouri.
FEMA:
Applications for the ARRA fire station construction were due July 10, 2009
DHS MGMT:
GSA executed a “Right of Entry” agreement with DC to allow construction access to the West Campus for Phase 1 development off of Firth Sterling Avenue. This is a critical milestone to allow demolition and site development activities to proceed on schedule. GSA held a Kick-off meeting for the Tier 2 National Environmental Policy Act (NEPA) analysis and master planning for the DHS office space to be housed on the St. Elizabeths East Campus. This effort will support the timely GSA execution of DHS ARRA funds programmed to design the new FEMA HQ on the East Campus.
CBP:
Tactical Communications: - No new actions taken to report this week. Non-Intrusive Inspection (NII): - No new actions taken to report this week.